## phase2_gate_checklist
gate_id | gate_name | status | evidence_file | evidence_note | owner | next_action | Template Needed | Evidence Missing | Generate in Word
P2-ENTRY-LOCK | Phase1 gates verified | Pending | nbs/Documentation/initial_conditioning_specsheet_scan.txt | Confirm all Phase1 exits are still valid | owner | Verify latest gate artifacts | General Template | TRUE | No
P2-ROUTE-INHERITANCE | Frozen CONTROL-routed path enforced | Pending | saragen0/SARA.Gen0.Client/SARAClient.cs | Client route path is CONTROL-first | owner | Add final proof note | General Template | TRUE | No
P2-SECURITY-STATE-COVERAGE | allow/deny/constrain/schema-fail represented | In Progress | saragen0/SARA.Gen0.UI/Phase2Personality.cs | Persona state mapping added for outcomes | owner | Wire UI templates to all response views | General Template | FALSE | No
P2-NON-AUTH-PRESERVATION | UI cannot mutate authority decisions | In Progress | saragen0/SARA.Gen0.UI/Phase2Personality.cs | Safety-state fallback keeps route/gate truth | owner | Add explicit non-authority banner in UI | General Template | FALSE | No
P2-PERSONA-EVOLUTION-SAFETY | Persona inputs remain presentation-scoped | Pending | nbs/Documentation/phase2_finish_off_plan.txt | Spec-constrained target defined | owner | Implement preference persistence rules | Persona Template | TRUE | No
P2-ACCESSIBILITY-READABILITY | Plain-language fallback and readability constraints | In Progress | saragen0/SARA.Gen0.UI/Phase2Personality.cs | Safety fallbacks produce guidance-first text | owner | Tune templates and run review | General Template | FALSE | No
P2-SYNTHETIC-CUSSING-SAFETY | Synthetic phrasing bounded and safe | Pending | nbs/Documentation/phase2_finish_off_plan.txt | No explicit bounded phrase list yet | owner | Add bounded phrase list and disable-in-safety rule | General Template | TRUE | No
P2-ARTIFACT-ALIGNMENT | Frozen artifact set only | Pending | nbs/Documentation/initial_conditioning_discovery.txt | Post-phase lock documented | owner | Attach artifact verification evidence | General Template | TRUE | Yes
P2-CREATIVITY-BOUNDED-TESTABILITY | Creativity default-off unless permitted | Pending | nbs/Documentation/phase2_finish_off_plan.txt | Rule documented but not wired in UI | owner | Implement mode toggle with gate dependency | Creativity Template | TRUE | No
P2-NON-AUTONOMY-ENFORCEMENT | No autonomy-like behavior possible | Pending | nbs/Documentation/phase2_finish_off_plan.txt | Constraint documented | owner | Add explicit UI policy statement | General Template | TRUE | No
P2-CREATIVITY-ROUTE-GATE-OSH-INTEGRITY | Creativity remains routed/gated/OSH-safe | Pending | nbs/Documentation/initial_conditioning_architecture_scan.txt | Architecture path confirmed | owner | Link runtime evidence | Creativity Template | TRUE | Yes
P2-CREATIVE-ADA-SAFETY-VERIFICATION | ADA safety verified in creative and non-creative modes | Pending | nbs/Documentation/phase2_finish_off_plan.txt | Verification pending | owner | Create validation checklist | Safety Template | TRUE | No
📝 WORD TEMPLATES TO GENERATE |  |  |  |  | 📊 WORK TYPE SUMMARY
Gate ID | Gate Name | Template Needed | Owner |  | Work Type | Count
P2-ARTIFACT-ALIGNMENT | Frozen artifact set only | General Template | owner |  | Excel Work (Evidence Missing) | 9
P2-CREATIVITY-ROUTE-GATE-OSH-INTEGRITY | Creativity remains routed/gated/OSH-safe | Creativity Template | owner |  | Word Work (Generate in Word) | 2
[5 empty] | Pending Status Items | 9
[5 empty] | In Progress Items | 3
🎨 STATUS COLOR LEGEND
[5 empty] | ⬜ Pending | Needs attention - Red
[5 empty] | ⬜ In Progress | Work ongoing - Yellow
[5 empty] | ⬜ Complete | Done - Green
[5 empty] | ⬜ Generate in Word = Yes | Needs Word doc - Blue
💡 TIP: Set 'Generate in Word' to 'Yes' for items that need Word documentation. The summary table above will automatically list those items with their required templates.